## MASTER DASHBOARD
VULNERABILITY & PENTESTING PROJECT MANAGEMENT
Last Updated: 2025-11-14 18:50:33
REAL-TIME KEY PERFORMANCE INDICATORS
CRITICAL | HIGH | MEDIUM | LOW | TOTAL ACTIVE | RESOLVED | OPEN % | RESOLUTION RATE
2 | 2 | 1 | 0 | 5 | 1 | 62.5% | 12.5%
PROJECT BREAKDOWN |  |  | STATUS DISTRIBUTION |  |  | SLA COMPLIANCE |  |  | RISK METRICS
Project Type | Count | Status | Status | Count | % | Priority | On Track | At Risk | Metric | Value | Target
Penetration Test | 4 | ⚠ Active | Active | 5 | 62.5% | Critical | 2 | 0 | Avg CVSS | 7.9 | 7.0
Vulnerability Assessment | 2 | ⚠ Active | In Review | 1 | 12.5% | High | 2 | 1 | Crit/High | 6 | <5
Code Review | 1 | ✓ Complete | Resolved | 1 | 12.5% | Medium | 2 | 0 | Fix Rate % | 12.5% | 80%
Infrastructure Test | 1 | ⚠ Active | Deferred | 1 | 12.5% | Low | 0 | 0 | SLA Compliance % | 75% | 95%

## DATA (hidden)
ID | Project Type | Project Name | Description | Severity | Finding Type | Owner | CVSS Score | Category | Status | Status Type | SLA Status | Days to Resolve | Found Date | Target Date
F-001 | Penetration Test | ACME Corp Web App | SQL Injection in login form | Critical | Code | John Smith | 9.8 | Injection | Active | Active | On Track | 5 | 2025-11-04 18:51 | 2025-11-19 18:51
F-002 | Penetration Test | ACME Corp Web App | XSS vulnerability in dashboard | High | Code | John Smith | 7.5 | XSS | Active | Active | At Risk | 2 | 2025-11-06 18:51 | 2025-11-16 18:51
F-003 | Vulnerability Assessment | TechCorp Infrastructure | Unpatched SSH service | High | Patch | Jane Doe | 8.1 | Patch Management | Active | Active | On Track | 10 | 2025-11-09 18:51 | 2025-11-24 18:51
F-004 | Penetration Test | ACME Corp Web App | Weak password policy | Medium | Configuration | John Smith | 5.3 | Authentication | In Review | In Review | On Track | 8 | 2025-11-02 18:51 | 2025-11-22 18:51
F-005 | Code Review | DevCorp Mobile App | Hardcoded credentials in source | Critical | Code | Mike Brown | 9 | Credentials | Resolved | Resolved | On Track | 3 | 2025-10-15 18:51 | 2025-10-18 18:51
F-006 | Vulnerability Assessment | TechCorp Infrastructure | Default credentials on router | Critical | Configuration | Jane Doe | 9.2 | Access Control | Active | Active | Overdue | 15 | 2025-10-30 18:51 | 2025-11-11 18:51
F-007 | Penetration Test | ACME Corp Web App | CSRF in account settings | Medium | Code | John Smith | 6.5 | CSRF | Active | Active | On Track | 4 | 2025-11-08 18:51 | 2025-11-18 18:51
F-008 | Infrastructure Test | TechCorp Network | Open SMB shares | High | Configuration | Jane Doe | 7.8 | Data Exposure | Deferred | Deferred | On Track | 40 | 2025-10-25 18:51 | 2025-12-24 18:51

## ANALYTICS
ADVANCED ANALYTICS & REPORTING
SEVERITY DISTRIBUTION |  |  |  | FINDING CATEGORIES |  |  |  | BY PROJECT TYPE
Critical | 3 | 37.5% |  | Injection | 1 | 14.29% |  | Penetration Test | 4 | 0
High | 3 | 37.5% |  | XSS | 1 | 14.29% |  | Vulnerability Assessment | 2 | 0
Medium | 2 | 25% |  | Authentication | 1 | 14.29% |  | Code Review | 1 | 1
Low | 0 | 0% |  | Patch Management | 1 | 14.29% |  | Infrastructure Test | 1 | 0
|  |  |  | Data Exposure | 1 | 14.29%
|  |  |  | Configuration | 0 | 0%
|  |  |  | Credentials | 1 | 14.29%
|  |  |  | CSRF | 1 | 14.29%
KEY METRICS & KPIs |  |  |  | MONTHLY METRICS
Total Findings | 8 | 📈 |  | Findings Found | 5
Critical Count | 3 | 📉 |  | Resolved This Month | 0
Average CVSS | 7.9 | 📈 |  | Still Active | 5
Resolved | 1 | 📉 |  | Resolution % | 0%
Active | 5 | 📈
Resolution Rate | 12.5% | 📉
Avg Days to Fix | 10.875 | 📈
SLA On Track % | 75% | 📉
CRITICAL & HIGH PRIORITY FINDINGS (Auto-Sorted)
ID | Project | Description | Severity | Category | Owner | CVSS | Status | SLA | Days Open | Target | Action
0 | 0
- | -
- | -
- | -
- | -

## PROJECT TRACKER
PROJECT & ENGAGEMENT TRACKING
Active Projects
Project ID | Project Name | Type | Client | Team Lead | Start Date | End Date | Status | Critical | High | Medium | Progress
P-001 | ACME Corp - Web Application PT | Penetration Test | ACME Corp | John Smith | 2025-11-09 18:51 | 2025-11-23 18:51 | Active | 1 | 3 | 5 | 65%
P-002 | TechCorp - Infrastructure VA | Vulnerability Assessment | TechCorp | Jane Doe | 2025-11-12 18:51 | 2025-11-26 18:51 | Active | 2 | 2 | 4 | 35%
P-003 | DevCorp - Code Review | Code Review | DevCorp | Mike Brown | 2025-11-04 18:51 | 2025-11-16 18:51 | In Progress | 0 | 2 | 3 | 85%

## SETTINGS
SYSTEM SETTINGS & REFERENCE
STATUS LEGEND
Active | Vulnerability identified & being fixed
In Review | Pending review/approval
Resolved | Fixed and verified
Deferred | Scheduled for later
SEVERITY GUIDE
Critical | CVSS: 9.0-10.0 | SLA: 24 hours
High | CVSS: 7.0-8.9 | SLA: 3-5 days
Medium | CVSS: 4.0-6.9 | SLA: 2-4 weeks
Low | CVSS: 0.1-3.9 | SLA: 1-3 months

## PENTEST CHECKLIST
PENETRATION TESTING METHODOLOGY & CHECKLIST
OWASP TOP 10 TESTING COVERAGE |  |  |  | TESTING PHASES
A1: Broken Access Control | ☐ Test | ☐ Found | 0 | Reconnaissance | ✓
A2: Cryptographic Failures | ☐ Test | ☐ Found | 0 | Scanning | ✓
A3: Injection | ☐ Test | ☐ Found | 0 | Enumeration | ○
A4: Insecure Design | ☐ Test | ☐ Found | 0 | Exploitation | ○
A5: Security Misconfiguration | ☐ Test | ☐ Found | 0 | Reporting | ○
A6: Vulnerable Components | ☐ Test | ☐ Found | 0
A7: Authentication Failures | ☐ Test | ☐ Found | 0
A8: Data Integrity Failures | ☐ Test | ☐ Found | 0
A9: Logging & Monitoring | ☐ Test | ☐ Found | 0
A10: SSRF | ☐ Test | ☐ Found | 0

## EXPORT & TEMPLATES
REPORT GENERATION & EXPORT
QUICK EXPORT FORMULAS
Total Findings | Copy to PowerPoint
Critical Count | For Executive Summary
High Issues | For Risk Assessment
Avg CVSS | Overall Risk Score
Resolution Rate % | Show Progress
SLA Compliance % | Compliance Metric

## QUICK REFERENCE
QUICK REFERENCE GUIDE
DASHBOARD TAB GUIDE
MASTER DASHBOARD | Real-time KPIs, Status, SLA, Risk metrics - START HERE
ANALYTICS | Detailed analysis, trends, monthly metrics, top findings
PROJECT TRACKER | Active projects, engagement tracking, team assignments
PENTEST CHECKLIST | OWASP Top 10, testing phases, methodology
EXPORT & TEMPLATES | Report templates, quick reference data
SETTINGS | Legend, definitions, severity guide
KEY FORMULAS
Critical Count | #NAME?
Resolution Rate | #NAME?
SLA Status | Auto-calculates On Track/At Risk/Overdue
Avg CVSS | #VALUE!
Monthly Trends | #VALUE!